## Slide 1
Risk Analysis of a Nuclear Power Plant Project
Arthur Gailes, Eleanya Onuma, Henry Castellanos, Tim Smythe
November 2, 2016

## Slide 2
Executive Summary
We conducted an initial risk analysis for a 1,000MW nuclear power plant project, where the investor is a privately-owned utility operating in a competitive wholesale electricity market
Given the extended project timeframe (60+ years), value is expressed in NPV terms, comprising upfront capital costs, annual operating profits, and back-end decommissioning costs
We considered a broad range of revenue and cost uncertainties that influence NPV. Sensitivity analysis identified four (construction cost, construction time, electricity price, capacity factor) as most impactful.
Distributions were fitted to historical data on key uncertainties as a basis for Monte Carlo simulation
The Monte Carlo model yields an expected positive NPV of $298M, but also a significant probability (34%) of a negative NPV outcome, and a VAR0.05 risk measure of -$3.8B NPV
Assuming a Bernoulli utility function with constant risk aversion, the certain equivalent for this risky project is $42M, suggesting a risk premium of $256M
Prior to reaching a project investment decision, we advise investing in more information that could help narrow the range of uncertainty on overnight construction costs, a key driver of downside risk

## Slide 3
Nuclear power plants are long-development and long-life infrastructure projects with many inherent risks
Source: Edward Kee. Nuclear Power Plant Business Models. Nera Economic Consulting. 2014.

## Slide 4
Financing Decision
Investment Decision
Cost of Debt
Cost of Equity
Total Capital Cost
Value (NPV)
Annual
Operating Cost
Decomm-issioning Cost
Annual
Revenue
O&M
Fuel
Uranium Price
Overnight Cost
Const. Time
Plant Lifespan
Plant Capacity
Capacity Factor
Electricity Price
Market Supply
Market Demand
Outages
Weather
Economic Conditions
Energy Policy
Const.Labor
Materials
Regulatory Delay
Construction Delay
Plant Labor
Upfront capital investment and operating profits depend on a wide range of underlying uncertainties

## Slide 5
Financing Decision
Investment Decision
Cost of Debt
Cost of Equity
Capital Cost
Value (NPV)
Annual
Operating Cost
Decomm-issioning Cost
Annual
Revenue
O&M
Fuel
Overnight Cost
Const. Time
Plant Lifespan
Plant Capacity
Capacity Factor
Electricity Price
Through node reduction we can focus on a narrower set, some of which we know in advance or can predict with high confidence
Accrued interest during construction
Discount rate
Operator design choice
Assumed = 1,000MW
New nuclear plants are designed for a 60-year life
Operating and maintenance costs exhibit low volatility and are consistent across the industry
Depends on the investor’s known cost of capital

## Slide 6
Base Case
Construction Overnight Cost
5th Percentile
95th Percentile
5th Percentile
95th Percentile
5th Percentile
95th Percentile
5th Percentile
95th Percentile
5th Percentile
95th Percentile
Electricity Price
Construction Time
Capacity Factor
Fuel Costs
Decommission Cost
9% of OCC
15% of OCC
Selection of uncertainties for Monte Carlo Simulation
Among remaining uncertainties, project NPV is most sensitive to construction cost and time, electricity price and capacity factor
Note: The Base Case assumes all variables are at their historical means.

## Slide 7
The value function incorporates simulated and deterministic variables
NPV = - Capital Costs + NPV Operating Profit – NPV Decommissioning
Total Capital Costs =
(including financing costs)
Operating NPV =
Decommissioning NPV =
Where Gen = Annual Generation in MWh = 1,000MW * 8,760hrs/yr * Capacity Factor
Where OCC = Overnight Construction Costs in $/kW
n = Construction time in years
Where P = Decommissioning costs as a % of overnight capital costs
Assumes decommissioning costs are fully incurred in the year following plant closure (year 61)
Assumptions
Plant capacity = 1,000MW
Plant life = 60 yrs.
r = .07 (interest rate and discount rate)
Variable O&M = $2.14/MWh
Fixed O&M = $93.3M/yr
Fuel Cost = $6.17/MWh
P = 12%
= Simulated Variable
This formulation of the value function makes certain simplifying assumptions. It is a pre-tax model that ignores the complexities of tax credits and subsidies common in the nuclear energy industry. The model also assumes zero inflation in electricity prices and operating costs over the 60 year operating period.

## Slide 8
Nearly 50 years of global nuclear construction data were used to fit distributions for overnight costs and construction time
Overnight Construction Costs (OCC)
Data Source: The Breakthrough Institute, “Historical construction costs of global nuclear power reactors,” 2015.
Note: To be consistent with observed historical ranges, the OCC distribution is truncated at $11,000 and the construction time distribution is truncated at 25 years.
OCC - $/kW
OCC - $/kW
Log-Gamma Distribution
- Parameters & Fit Statistics -
Log-Gamma Distribution
  Est. SE
  Shapelog: 204.9 15.4
  Ratelog: 26.5 2.0
  Loglikelihood: -3000.2
  AIC: 6004.4
  BIC: 6012.2
Construction Time
Years
Years
Inverse Weibull
- Parameters & Fit Statistics -
  Est. SE
  Shape: 3.27 .14
  Scale: 5.68 .10
  Loglikelihood: -809.2
  AIC: 1622.5
  BIC: 1630.2
Inverse Weibull Distribution

## Slide 9
To model revenue, distributions were fitted to historical U.S. data on plant capacity factor and wholesale electricity prices
Capacity Factor
Data Sources: Plant-level capacity factors, 2008-2015, from Nuclear Regulatory Commission, Information Digest, Appendix A; Average annual wholesale electricity prices, 2001-2015, PJM West hub from US Energy Information Administration.
Capacity Factor
Weibull Distribution
- Parameters & Fit Statistics -
Weibull Distribution
  Est. SE
  Shape: 11.9 .34
  Scale: .94 .002
  Loglikelihood: 752.5
  AIC: -1501.0
  BIC: -1491.7
Wholesale Electricity Prices
Inverse-Para-Logistic
- Parameters & Fit Statistics -
  Est. SE
  Shape: 5.4 1.03
  Scale: 35.2 1.96
  Loglikelihood: -59.1
  AIC: 122.3
  BIC: 123.7
Inverse-Para-Logistic Distribution
Capacity Factor
Electricity prices
Electricity prices

## Slide 10
The expected NPV is positive, but the distribution is negatively skewed. Alternative formats of the risk curve aid interpretation of upside and downside risk.
NPV Distribution from Monte Carlo Simulation
Mean NPV = $298M
VAR0.05 = ($3.8B)

## Slide 11
Bernoulli Utility Function:
Expected NPV of Project:
Expected Utility of Project
Certain Equivalent (CE):
, so that NPV = $0.042Bn or $42m
Risk Premium:
Based on the utility function, our firm will be indifferent between receiving $42m with certainty or $298m in expectation. If the power plant project is pursued, we will be willing to pay <= $256m as an insurance premium.
Utility Curve is concave, typical of risk aversion
We assume that our firm is risk averse and measure preferences with a Bernoulli Utility Function

## Slide 12
Areas for further analysis
Given the scale of investment and range of potential outcomes, we recommend investing in additional information
  Historical global overnight construction costs (the basis for our simulation distribution) vary widely and account for much of the variation in project NPV. A more detailed planning exercise that specifies the reactor technology and estimates the labor and materials costs for a particular plant design in the local market could substantially decrease the range of uncertainty on capital costs.
  Electricity prices and plant capacity factor are a function of competition from other energy sources. The historical data used in our model may not accurately approximate the level of future uncertainty in these variables if the market context shifts significantly (e.g. policy decisions to put a price on carbon emissions or subsidies for renewables).
  Evaluation of alternative investment opportunities to inform decision making on whether or not to invest in the nuclear power project